## 7020 release note
Descriprion | Date of fix | FW version | Deadline | NAG Feedback | Remark
During the call indication of incoming 2-nd call very laud. Need abolity to adjust it in web interface | 2011-05-23 | 2.0.2.20 | 2011-05-21 |  | add a on/off switch on web, check on Phone-Call Feature-call waiting. If not enabled, while talking, 2-nd incoming call will hear busy tone. If enabled, 2-nd incoming call will display on LCD, you could press FL to pick up, the first talking call will be put on hold
Ringtone not work | 2011-05-23 | 2.0.2.20 | 2011-05-21
If we have MissedCall, and take handset - volume in handset reduces by a half | 2011-05-23 | 2.0.2.20 | 2011-06-01
No way to change ringtone via MENU | 2011-05-14 | 2.0.2.18 |  | OK
need autoprovisioning function | 2011-05-14 | 2.0.2.18 | 2011-06-01 | need ability to update config file |  | hold it while not solve freeze issue/VLAN issue
bilingual display, English + Russian | 2011-05-03 | 2.0.2.17 |  | only web, phone display will be implememted shortly. LCD could display Russian, too | hold
Phone freezes after about 20 hours | 2011-05-03 | 2.0.2.17 |  | OK |  | phone freezes still occurs when connected with PC
Phone freeze when pick up handset, input number, # or Redial to call out | 2011-05-03 | 2.0.2.17 |  | OK
Fast dial via memory keys not work. Phone crached | 2011-05-03 | 2.0.2.17 |  | OK | Press M*, then press # to dial out
Callout via phone book not work | 2011-05-03 | 2.0.2.17 |  | OK | Choose a contact, press # to callout
Callout via MissedCalls causes phone crash | 2011-05-03 | 2.0.2.17 |  | OK
ability to dial out from SIP2 | 2011-05-03 | 2.0.2.17 | testing | can't work when long numbers set |  | not work
Edit display name of SIP account, digits behind space bar disappear | 2011-04-11 | 2.0.2.12 |  | OK
First line of LCD display can be edited. Check on Web-Wan | 2011-04-11 | 2.0.2.12 |  | OK
In edit name (like in phone book), space bar is added on 0 key | 2011-04-11 | 2.0.2.12 |  | OK
Caller ID of incoming calls | 2011-04-11 | 2.0.2.12 | 2011-06-01 | some display is wrong
Ringer volume adjustable from website | 2011-04-11 | 2.0.2.12 |  | OK
First power on, pick up handset, dial out, the phone changes to HF | 2011-04-11 | 2.0.2.12 |  | OK
HF issue. When activated, the opposite side can't hear well |  |  |  | OK | hw issue, solved by revising hw
Sometimes handset volume reduces to minimum. When we try to increase it - volume restored |  |  |  |  | Testing
sometimes the phone can't hang up. put the handset back, the phone keeps ringing "bip bip bip |  |  |  |  | Testing
Need ability to upload ringtone to the phone |  |  |  |  | not possible, more ringers could be implememted
WMI indication abt voice messages |  |  | 2011-06-01 |  | make it blink when there's voice msg
Need ability to remote reset the phone via Telnet/SNMP/etc.enter command like "reset" and phone must be reset. Via web interface - not comfortable |  |  |  |  | need to change base codes, too much work. We have implemented manually reset. Press # when power on, press*#168 to reset | hold it while not solve freeze issue/VLAN issue
If we use headset sensetivity of MIC is low, our opponent hear us very bad. Need to increase volume to solve it. Looks like old problen with handset. If we use handset - there is no such problem |  |  |  |  | not very clear, pls provide more details | very bad sensetivity of MIC if we try to use HEADset, our opponent hear us very bad
Is it possible to indicate CallerID info as running line? Because there are many Russian names like: "Габдурахманова Алевтина". Too long line. Need indicate it like running line |  |  | 2011-06-01
Some of our customers feedback abt wrong CallerID indication. For example Caller ID name "Салькова Вера" looks like "алькова Верааари" |  |  | 2011-06-01
Phone freez(after 20 hours) issue not fixed if phone work as a bridge (PC host connected to LAN port) |  |  |  |  | testing
When handset picked up, can call out from call log, phonebook, speed dial keys |  |  |  |  | testing
Router + NAT |  |  | 2011-06-30